## Sheet1
Project_name | Engineer | 01-Project Development | 02-Purchasing | 03-Manufacturing | 04-Assembly | 05-Machine Start-up | 06-Team Buy-off | 07-Status
Customer Program Name | Everton Rodrigues |  | 0 | 0 | 0 |  | 0 | 0
M_22_065 - Webbing Cut + Transfer + Pin Sewing | Everton Rodrigues | 100 | 100 | 100 | 100 | 100 | 100 | 0
M_22_069 - Webbing Cut + Transfer + Pin Sewing | Everton Rodrigues | 100 | 100 | 100 | 100 | 46 | 0 | -149
M_22_073 - Webbing Cut + Transfer + Pin Sewing | Everton Rodrigues | 100 | 100 | 100 | 71 | 0 | 0 | -213
M_22_192 - Roll Folder | Everton Rodrigues | 83 | 100 | 100 | 100 | 100 | 100 | -131
M_23_027 - Band-it Crimping | Everton Rodrigues | 80 | 37 | 49 | 0 | 0 | 0 | -21
M_23_028 - Hardware Install | Everton Rodrigues | 74 | 46 | 22 | 0 | 0 | 0 | -127
M_23_064- Spindle Assy LLS | Everton Rodrigues | 74 | 34 | 48 | 0 | 0 | 0 | -47
M_23_065 - Thread Head Crimping LLS | Everton Rodrigues | 74 | 24 | 49 | 0 | 0 | 0 | -29
M_23_066 - Riveting Crimping | Everton Rodrigues | 74 | 29 | 49 | 0 | 0 | 0 | -23
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 38 | 0 | 0 | 0 | 0 | 0 | -23
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 33 | 0 | 0 | 0 | 0 | 0 | -25
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 29 | 0 | 0 | 0 | 0 | 0 | -28
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 42 | 0 | 0 | 0 | 0 | 0 | -18
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 32 | 0 | 0 | 0 | 0 | 0 | -25
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 35 | 0 | 0 | 0 | 0 | 0 | -22
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 27 | 0 | 0 | 0 | 0 | 0 | -29
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 27 | 0 | 0 | 0 | 0 | 0 | -29
R_23_059 Tooling Description | Everton Rodrigues | 100 | 100 | 100 | 100 | 100 | 100 | 0
T_23_035 - Compression Folder Tooling | Everton Rodrigues | 100 | 100 | 100 | 100 | 100 | 100 | 0
T_23_040 - Torque Nest | Everton Rodrigues | 73 | 100 | 100 | 100 | 100 | 0 | -131
T_23_052 - Deflector Install | Everton Rodrigues | 80 | 27 | 0 | 0 | 0 | 0 | -53
T_24_012 - Deco Switch Torque | Everton Rodrigues | 41 | 0 | 0 | 0 | 0 | 0 | -23
T_24_013 - Routing Wire harness | Everton Rodrigues | 41 | 0 | 0 | 0 | 0 | 0 | -23
T_24_014 - Riveting Crimping | Everton Rodrigues | 22 | 0 | 0 | 0 | 0 | 0 | -37
T_24_015 - Spring Assy & Easy Snap Check | Everton Rodrigues | 35 | 0 | 0 | 0 | 0 | 0 | -25
T_24_016 - Deco Switch Torque | Everton Rodrigues | 35 | 0 | 0 | 0 | 0 | 0 | -25
T_24_017 - Paddle & Ground Torque | Everton Rodrigues | 34 | 0 | 0 | 0 | 0 | 0 | -26
T_24_018 - ECU test | Everton Rodrigues | 35 | 0 | 0 | 0 | 0 | 0 | -25
T_24_019 - E-Check Test | Everton Rodrigues | 35 | 0 | 0 | 0 | 0 | 0 | -25
T_24_020 - Mylar and packaging | Everton Rodrigues | 22 | 0 | 0 | 0 | 0 | 0 | -34
M_23_025 - Thermo Wrapper | João Ribeiro | 100 | 100 | 100 | 100 | 94 | 0 | -59
M_YY_XXX - Machine Description | João Ribeiro | 100 | 100 | 100 | 100 | 96 | 0 | -65
M_24_024 - Machine Description | João Ribeiro | 0 | 0 | 0 | 0 | 0 | 0 | 0
M_24_025 - Machine Description | João Ribeiro | 1 | 0 | 0 | 0 | 0 | 0 | -66
M_24_026 - Machine Description | João Ribeiro | 17 | 0 | 0 | 0 | 0 | 0 | -42
M_24_030 - Machine Description | João Ribeiro | 17 | 0 | 0 | 0 | 0 | 0 | -42
M_24_032 - Machine Description | João Ribeiro | 17 | 0 | 0 | 0 | 0 | 0 | -42
T_23_050 - Torque & E-Check Nest | João Ribeiro | 100 | 100 | 100 | 100 | 32 | 0 | -45
T_YY_XXX - Tooling Description | João Ribeiro | 100 | 100 | 100 | 18 | 0 | 0 | -14
M_23_026 - Deck Roller | Marcelo Castro | 74 | 42 | 0 | 0 | 0 | 0 | -34
M_23_049 - Uni_Roller Folder | Marcelo Castro | 80 | 91 | 59 | 0 | 0 | 0 | -30
M_23_063 - ICAB bracket orbital riveting | Marcelo Castro | 72 | 34 | 0 | 0 | 0 | 0 | -33
M_24_001 - Accordion Folding Machine | Marcelo Castro | 64 | 23 | 0 | 0 | 0 | 0 | -32
T_22_187 - Compression Folder Fixture | Marcelo Castro | 100 | 90 | 100 | 100 | 0 | 0 | -63
T_23_047 - Band-it Crimping Honda 3UT | Marcelo Castro | 100 | 100 | 100 | 100 | 20 | 0 | -12
T_23_048 - Hardware Install Honda 3UT | Marcelo Castro | 100 | 100 | 100 | 100 | 20 | 0 | -12
T_23_057 - Band-it Crimping Nest | Marcelo Castro | 66 | 53 | 29 | 0 | 0 | 0 | 22
M_24_021 - Deflector Install - KAB Toyota 640AX | Rodrigo Santos | 27 | 0 | 0 | 0 | 0 | 0 | -14
M_24_022 - Kab Folding - KAB Toyota 640AX | Rodrigo Santos | 26 | 0 | 0 | 0 | 0 | 0 | -21
M_24_023 - Torque and Assembly - KAB Toyota 640AX | Rodrigo Santos | 25 | 0 | 0 | 0 | 0 | 0 | -16