## Sheet1
Project_name | Engineer | 01-Project Development | 02-Purchasing | 03-Manufacturing | 04-Assembly | 05-Machine Start-up | 06-Team Buy-off
Customer Program Name | Everton Rodrigues | 0 | 0 | 0 | 0 | 0 | 0
M_22_065 - Webbing Cut + Transfer + Pin Sewing | Everton Rodrigues | 0 | 0 | 0 | 0 | 0 | 0
M_22_069 - Webbing Cut + Transfer + Pin Sewing | Everton Rodrigues | 0 | 0 | 0 | 0 | 0.54 | 0
M_22_073 - Webbing Cut + Transfer + Pin Sewing | Everton Rodrigues | 0 | 0 | 0 | 0.29 | 0 | 0
M_22_192 - Roll Folder | Everton Rodrigues | 0.17 | 0 | 0 | 0 | 0 | 0
M_23_027 - Band-it Crimping | Everton Rodrigues | 0.2 | 0.63 | 0.51 | 0 | 0 | 0
M_23_028 - Hardware Install | Everton Rodrigues | 0.26 | 0.54 | 0.78 | 0 | 0 | 0
M_23_064- Spindle Assy LLS | Everton Rodrigues | 0.26 | 0.66 | 0.52 | 0 | 0 | 0
M_23_065 - Thread Head Crimping LLS | Everton Rodrigues | 0.26 | 0.76 | 0.51 | 0 | 0 | 0
M_23_066 - Riveting Crimping | Everton Rodrigues | 0.26 | 0.71 | 0.51 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.62 | 0 | 0 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.67 | 0 | 0 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.71 | 0 | 0 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.58 | 0 | 0 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.68 | 0 | 0 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.65 | 0 | 0 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.73 | 0 | 0 | 0 | 0 | 0
MXMA J4U SW - Flexible Assy Line | Everton Rodrigues | 0.73 | 0 | 0 | 0 | 0 | 0
R_23_059 Tooling Description | Everton Rodrigues | 0 | 0 | 0 | 0 | 0 | 0
T_23_035 - Compression Folder Tooling | Everton Rodrigues | 0 | 0 | 0 | 0 | 0 | 0
T_23_040 - Torque Nest | Everton Rodrigues | 0.27 | 0 | 0 | 0 | 0 | 0
T_23_052 - Deflector Install | Everton Rodrigues | 0.2 | 0.73 | 0 | 0 | 0 | 0
T_24_012 - Deco Switch Torque | Everton Rodrigues | 0.59 | 0 | 0 | 0 | 0 | 0
T_24_013 - Routing Wire harness | Everton Rodrigues | 0.59 | 0 | 0 | 0 | 0 | 0
T_24_014 - Riveting Crimping | Everton Rodrigues | 0.78 | 0 | 0 | 0 | 0 | 0
T_24_015 - Spring Assy & Easy Snap Check | Everton Rodrigues | 0.65 | 0 | 0 | 0 | 0 | 0
T_24_016 - Deco Switch Torque | Everton Rodrigues | 0.65 | 0 | 0 | 0 | 0 | 0
T_24_017 - Paddle & Ground Torque | Everton Rodrigues | 0.66 | 0 | 0 | 0 | 0 | 0
T_24_018 - ECU test | Everton Rodrigues | 0.65 | 0 | 0 | 0 | 0 | 0
T_24_019 - E-Check Test | Everton Rodrigues | 0.65 | 0 | 0 | 0 | 0 | 0
T_24_020 - Mylar and packaging | Everton Rodrigues | 0.78 | 0 | 0 | 0 | 0 | 0
M_23_025 - Thermo Wrapper | João Ribeiro | 0 | 0 | 0 | 0 | 0.06 | 0
M_YY_XXX - Machine Description | João Ribeiro | 0 | 0 | 0 | 0 | 0.04 | 0
M_24_024 - Machine Description | João Ribeiro | 0 | 0 | 0 | 0 | 0 | 0
M_24_025 - Machine Description | João Ribeiro | 0.99 | 0 | 0 | 0 | 0 | 0
M_24_026 - Machine Description | João Ribeiro | 0.83 | 0 | 0 | 0 | 0 | 0
M_24_030 - Machine Description | João Ribeiro | 0.83 | 0 | 0 | 0 | 0 | 0
M_24_032 - Machine Description | João Ribeiro | 0.83 | 0 | 0 | 0 | 0 | 0
T_23_050 - Torque & E-Check Nest | João Ribeiro | 0 | 0 | 0 | 0 | 0.68 | 0
T_YY_XXX - Tooling Description | João Ribeiro | 0 | 0 | 0 | 0.82 | 0 | 0
M_23_026 - Deck Roller | Marcelo Castro | 0.26 | 0.58 | 0 | 0 | 0 | 0
M_23_049 - Uni_Roller Folder | Marcelo Castro | 0.2 | 0.09 | 0.41 | 0 | 0 | 0
M_23_063 - ICAB bracket orbital riveting | Marcelo Castro | 0.28 | 0.66 | 0 | 0 | 0 | 0
M_24_001 - Accordion Folding Machine | Marcelo Castro | 0.36 | 0.77 | 0 | 0 | 0 | 0
T_22_187 - Compression Folder Fixture | Marcelo Castro | 0 | 0.1 | 0 | 0 | 0 | 0
T_23_047 - Band-it Crimping Honda 3UT | Marcelo Castro | 0 | 0 | 0 | 0 | 0.8 | 0
T_23_048 - Hardware Install Honda 3UT | Marcelo Castro | 0 | 0 | 0 | 0 | 0.8 | 0
T_23_057 - Band-it Crimping Nest | Marcelo Castro | 0.34 | 0.47 | 0.71 | 0 | 0 | 0
M_24_021 - Deflector Install - KAB Toyota 640AX | Rodrigo Santos | 0.73 | 0 | 0 | 0 | 0 | 0
M_24_022 - Kab Folding - KAB Toyota 640AX | Rodrigo Santos | 0.74 | 0 | 0 | 0 | 0 | 0
M_24_023 - Torque and Assembly - KAB Toyota 640AX | Rodrigo Santos | 0.75 | 0 | 0 | 0 | 0 | 0